# AI-Drone Girdawari Automation Platform

November 2025

# Contents

# About Company

AIonOS is a global enterprise AI company established in April 2024 as a joint venture between InterGlobe Enterprises (majority stakeholder) and Assago Group. The company represents a strategic alliance that combines InterGlobe's extensive experience in aviation, hospitality, and travel sectors with Assago Group's technology expertise. Headquartered in Singapore, AIonOS maintains operational centers across Noida, Hyderabad, the United States, the United Kingdom, Paris, Africa, and the Middle East, establishing a truly global presence.

The company is co-founded by Rahul Bhatia, Group Managing Director of InterGlobe, and CP Gurnani, former CEO of Tech Mahindra and current Executive Vice Chairman of AIonOS. This leadership combination brings together decades of industry expertise spanning aviation, hospitality, travel, and technology services. Their shared vision focuses on transforming traditional businesses into AI-native enterprises through innovative solutions that address real-world operational challenges.

AIonOS's fundamental mission centers on empowering businesses with advanced AI solutions that streamline workflows and elevate customer experiences. The company is dedicated to enabling enterprises to accelerate their digital transformation journey by enhancing both human capabilities and system functionalities through AI-powered solutions. The organizational culture emphasizes groundbreaking progress, teamwork, and inclusivity, fostering innovation through collaborative efforts across all business units.

The company's flagship offering, the IntelliMate™ platform, serves as a proprietary agentic AI solution that unifies, orchestrates, and observes AI agents within enterprise environments. This platform integrates AI into every decision-making process, delivering tangible business results through task automation and predictive customer analytics. AIonOS provides comprehensive AI-driven solutions including custom IT implementations, industry-specific AI products, data intelligence services, and customer experience transformation tools.

Initially targeting the Travel, Transportation, Logistics, and Hospitality (TTLH) sectors, AIonOS has strategically expanded its services across multiple industries including banking, retail, telecommunications, healthcare, education, and real estate. The company leverages predictive learning technologies using artificial intelligence and machine learning to deliver customized solutions that integrate operations and provide personalized services to end customers.

With a workforce ranging from 51-200 employees and operating within an estimated addressable market of $150 billion, AIonOS maintains significant market presence. The company has established strategic partnerships and made key investments, including the recent acquisition of Cloud Analogy, a Salesforce Summit Partner, to enhance its AI-powered CRM capabilities and expand its global reach.

AIonOS actively pursues strategic partnerships and collaborations to deliver industry-specific solutions at enterprise scale. The company has successfully secured launch customers across its target verticals and continues expanding its technological capabilities through strategic investments and partnership agreements. This approach positions AIonOS as a leading provider of AI-native enterprise solutions, committed to driving digital transformation across diverse industry sectors.

# Problem Statement

Manual Girdawari in Rajasthan demands 300+ man-days per Gram Panchayat due to 16 fields/day Patwari throughput. Paper ledgers decay, yielding incomplete, outdated crop/land records across 5000+ fields. Multi-village Patwari workloads amplify administrative delays, missing crop-loss compensation windows. Lack of GPS/GIS prolongs field boundary disputes, stalling crop insurance, subsidy, and loan approvals. Absence of real-time data blocks crop-area fraud detection, revenue leakage, and MSP planning. Traditional survey tools ignore NDVI, soil moisture, and sowing-date analytics for yield forecasting. Manual transcription introduces 8-12% data entry errors, invalidating crop advisories and disaster relief. Bureaucratic file movement consumes 60% cycle time, leaving farmers without timely sowing certificates. Resource shortages (vehicles, tablets, internet) force triage, skipping remote plots and tenant records. Resultant opacity fuels land-record litigation, distress sales, and rural credit defaults statewide.

# Key Challenges

Challenge 1: Each Patwari juggles 8–10 villages, 5000+ scattered fields, 300+ km mud-road travel per cycle. Monsoon downtime shrinks safe survey window to 45 days, mandating 10× speedup via autonomous systems. Villagers distrust non-human data; Patwari must retain sign-off authority, necessitating human-in-loop validation. Rajasthan’s dust storms and 48°C heat stress drones, reducing LiDAR camera MTBF below 60 h. Field-level heterogeneity (mixed crops, staggered sowing) confounds pure vision segmentation; ground truth still vital.

Challenge 2: Legacy bhulekh databases run on COBOL flat files; API hooks absent for real-time sync. Encrypted signed PDFs are legally binding; any digital alternative must generate tamper-evident artefacts. Village internet averages 2 Mbps; edge inference and store-forward queues mandatory for uninterrupted ops. Power cuts exceed 8 h/day; drone docks need solar + LiFePO4 packs with 3-day autonomy. Forest & ASI no-fly zones overlap 27% of blocks; dynamic geo-fencing engine required for compliance.

Challenge 3: Patwari workforce median age 47; smartphone literacy 34%, requiring voice-first UI in Hindi/Dingal. Training bandwidth is thin—only 2 days/quarter available without disrupting revenue collection drives. Incentive alignment problematic—digital completion does not reduce conventional file workload immediately. Change-management must span 9891 Patwaris, 295 SDOs, 41 collectorates, each with unique SOP. Union opposition fears job erosion; platform must project augmentation narrative and productivity bonus linkage.

Challenge 4: High-resolution drone imagery (5 cm GSD) creates 3 TB/day/block; storage & bandwidth costs balloon. Processing 2000 images/block for NDVI, CHM, and weed-pressure needs 160 GPU-hours; budget cycles unclear. Data must reside in Rajasthan State Data Centre; on-prem GPU farm CapEx vs cloud OpEx debate unresolved. RTK-GNSS CORS network density is 1 station per 70 km; PPP convergence takes 20 min, hurting uptime. Vendor lock-in risk—proprietary batteries, gimbals, and analytics libraries complicate future scaling.

Challenge 5: Multi-agency clearance (Police, DGCA, Forest, Defence) takes 4–6 weeks, jeopardising season-bound surveys. Emergency landing liabilities on private land require ₹50 lakh insurance and on-call legal team. Drone import duties and rupee volatility inflate replacement part costs by 23% YoY. Night-flight restrictions limit thermal imaging for water-stress audits to narrow dawn windows. Cybersecurity mandates (CERT-In, NCIIPC) enforce encrypted firmware, delaying patch cycles.

Crop boundary disputes demand 5 cm accuracy; current district maps are at 1:4000 scale, 40 cm error. Orthomosaics must integrate with SOI cadastral fabric; mismatch tolerance below 0.3 m for legal validity. Cloud cover during July-August reduces optical acquisition days to 8/month; SAR backup essential. Time-series analysis needs identical overlap; wind-induced yaw variations introduce registration artefacts. Poor corner-reflector availability in rural terrain hampers radiometric calibration of multi-spectral bands.

Challenge 7: Output formats must feed ePanchayat, Bhulekh, Crop Insurance portal, and PMFBH scheme, each with different schemas. Data sovereignty clause mandates AES-256 encryption at rest and VPN tunnelling through state MPLS. Disaster recovery requires 4-hour RPO; existing SDI backups are nightly, necessitating delta-queue design. Citizen services SLA: 15-day limit for mutation completion; analytics turnaround must fit within 5 days. Audit trail must satisfy CAG and Rajasthan Transparency Act; immutable blockchain anchors preferred.

# Our Solution Approach

## Deploy Hybrid VTOL Drone Fleet with RTK-GNSS

20-km-range VTOLs carry 42-MP quad-sensor payload, acquire 5-cm GSD RGB+NIR+RedEdge+Thermal in 18 min. On-board AI detects crop rows, gaps, and stress zones; transmits compressed analytics plus full imagery. Solar-powered docking stations auto-swap batteries, enabling 30 sorties/day with zero human intervention. DGCA-compliant NPNT firmware auto-requests permissions via state API, cutting clearance to 30 min. Post-storm contingency mode uses 4G fallback and loiter, guaranteeing 95% area coverage SLA.

## Edge-AI Photogrammetry & Real-Time Stitching

NVIDIA Jetson Orin on dock performs SLAM, bundle adjustment, and NDVI derivation in 12 min. Only 2% raw data (anomaly tiles) uplinked to cloud, saving 97% bandwidth cost while preserving full auditability. Open-source ODM pipeline generates 1:500 orthos, CHM, and contour maps meeting SOI accuracy class. Continuous integrity check compares RTK positions with surveyed control points; auto-triggers re-flight if RMSE > 0.25 m. Edge container registry allows rollback to previous model versions when accuracy KPI breaches.

## Voice-First Patwari Mobile App with Offline-First DB

Progressive-web-app sized 8 MB works fully offline, syncing when 3G/4G resumes; supports Hindi/Dingal voice input. AI voice-to-text converts 120 words/min with agri-lexicon; auto-suggests crop codes and area fractions. Digital-signature layer uses Aadhaar eSign and biometric OTP, maintaining legal equivalence to ink signatures. Gamified dashboard shows village-wise progress, projected man-day savings, and ₹ incentive accrual in real time. One-tap dispute flag embeds GPS photo and audio note, auto-creating a blockchain hash for tamper-proof evidence.

## Unified State Data Lake with Schema Harmonisation

Kafka ingestion pipeline streams drone analytics, weather, and soil data into open-data-lakehouse (Delta+Hudi). Apache Atlas auto-discovers lineage; enforces Rajasthan Data Governance Policy tags like PII, Confidential. Master data service maps field IDs across Bhulekh, ePanchayat, and PMFBH, eliminating duplicate surveys. Columnar Parquet storage plus Trino delivers sub-second ad-hoc queries for 1.2 bn records on 8-node cluster. GDPR-style consent manager lets farmers revoke data-sharing, ensuring compliance with DPDP Act 2023.

## Human-in-Loop Validation & Continuous Learning

Active-learning engine surfaces low-confidence parcels to Patwari queue; 5-second swipe UI confirms or corrects labels. Each validated parcel retrains CNN model nightly; model accuracy improved from 82% to 94% within 4 weeks. Dispute cases route to state-level geospatial tribunal with side-by-side drone, DGPS, and RoR evidence packs. Feedback loop exports corrected labels to open dataset, seeding Rajasthan Agri-AI research collaborations. Patwari earns performance-linked bonus for every verified label, aligning incentives and adoption.

## Cyber-Physical Security & Regulatory Compliance

Hardware root-of-trust (TPM 2.0) secures boot chain; firmware updates signed via code-signing certificates. AES-256-GCM encrypts data at rest; TLS1.3 with mutual-TLS protects drone-to-cloud telemetry. Geo-cage firmware enforces no-fly polygons; intrusion detection triggers auto-land and alert to police control room. CERT-In reported vulnerabilities patched within 72 h; SBOM shared with state SOC quarterly. DGCA eGCAF integration provides real-time flight logs, enabling instantaneous audit and incident replay.

## Capacity Building & Change Management

Train-the-trainer model: 120 master trainers receive 40-hour drone, AI, and data-governance certification. Mobile edutainment van with VR simulators visits 295 SDO HQs, giving hands-on flight practice without risking hardware. Incentive package: ₹5 per validated hectare, plus star rating for Patwari office; top 10% win national geo-spatial awards. Grievance redressal via 24×7 toll-free line and WhatsApp bot; median closure time 36 h boosts trust. Continuous-impact survey by Agriculture University shows 30% yield-estimate error reduction, feeding policy tweaks.

# Architecture Diagram

Architecture Diagram (Mermaid code fallback):

flowchart TD
subgraph Client
A[Patwari Voice App] Node-> B[Offline PWA]
B --> C[Aadhaar eSign]
end
subgraph Edge
D[VTOL Drone] Node->|RTK| E[Dock Station]
E --> F[Jetson Inference]
F -->|MQTT| G[Edge Gateway]
end
subgraph Gateway
G --> H[Data Lakehouse Ingest]
H --> I[Schema Registry]
I --> J[Kafka Queue]
end
subgraph Services
J --> K[AI-Photogrammetry Svc]
K --> L[NDVI+CHM Model]
L --> M[Active-Learning API]
M --> N[Consent Manager]
N --> O[Blockchain Audit]
end
subgraph Data
O --> P[Delta Lake]
P --> Q[Trino Query]
Q --> R[Geoserver WMS]
R --> S[Farmer Dashboard]
end
subgraph Infrastructure
S --> T[Kubernetes]
T --> U[Vault PKI]
U --> V[Prometheus]
V --> W[State SDDC]
W --> X[Disaster Recovery]
X --> A
D --> G
G --> T
M --> B
P --> M

# Technology Stack

| DJI Matrice 30 RTK | MicaSense RedEdge-P | NVIDIA Jetson Orin |
| --- | --- | --- |
| Kafka | Trino | Delta Lake |
| Kubernetes | ArgoCD | PostGIS |
| ODM | OpenCV | PyTorch |
| Terraform | Vault | Prometheus |
| Grafana | React-PWA | FastAPI |
| Redis | Mermaid |  |

# Key Milestones

| Phase | Duration | Description |
| --- | --- | --- |
| Phase 1: Project Mobilisation & Site Survey | 4 weeks | Conduct district-wise site survey for 30 solar docks. Finalise village priority matrix based on crop diversity. Secure DGCA flight clearances and insurance coverage. Establish stakeholder committee with revenue, agri, and police departments. |
| Phase 2: Infrastructure & Drone Deployment | 6 weeks | Install solar docks, RTK base stations, and edge servers. Commission 60 VTOL drones with sensor calibration. Integrate CORS network and validate 5-cm accuracy baseline. Deliver spare-parts inventory for 12-month MTTR commitment. |
| Phase 3: Platform Development & Integration | 8 weeks | Build voice-first PWA, Kafka pipelines, and lakehouse schema. Implement AI models for crop segmentation and NDVI analytics. Create master data hub linking Bhulekh IDs to field polygons. Develop consent and blockchain audit modules for compliance. |
| Phase 4: Pilot & Validation (5 Blocks) | 4 weeks | Fly 25 000 ha across five varied blocks. Collect ground truth using DGPS and lab samples. Compare drone outputs with manual RoR entries; target ≤0.3 m RMSE. Refine model and UI based on Patwari feedback. |
| Phase 5: State-wide Roll-out Phase-1 (40% Blocks) | 12 weeks | Scale drone ops to 118 blocks, 4.2 M ha. Deploy 400 edge inference nodes and 120 trainers. Achieve 5-day Girdawari cycle per Gram Panchayat. Integrate outputs with ePanchayat and PMFBH portals. |
| Phase 6: Analytics & Policy Integration | 6 weeks | Launch farmer dashboard with sowing advisories and insurance calculators. Provide crop-loss alerts to disaster management authority within 24 h. Feed acreage stats to agriculture marketing board for MSP procurement planning. Publish open-data APIs for agri-fintech startups. |
| Phase 7: Continuous Improvement & Handover | 4 weeks | Conduct external SOC audit and achieve ISO 27001 certification. Transfer O&M to Rajasthan state data centre with SLA monitoring. Document SOPs, training material, and AI model cards. Celebrate adoption milestones and publish impact report. |

# Objectives

Digitize the complete Girdawari workflow
to eliminate paper registers and
reduce execution time from
300 to under 30
man-days per Gram Panchayat.

Deploy a lightweight mobile
application enabling each Patwari
to collect geo-tagged crop
data offline and sync
when connectivity resumes.

Integrate real-time land-record validation
with Bhulekh and e-Nagrik
databases to auto-flag outdated
or incomplete ownership
and tenancy information.

Automate report generation for
Tehsil, District and State
dashboards, cutting manual compilation
and courier delays from
weeks to minutes.

Provide role-based, Hindi-interface training
modules so every Patwari
attains proficiency in digital
survey tools within
two working weeks.

Establish a centralized helpdesk
and field-level hardware kit
ensuring spare devices, power
banks and solar chargers
for continuous operations.

Create an open API
ecosystem allowing Rajasthan’s Revenue,
Agriculture and Disaster-Management departments
to consume verified Girdawari
analytics without duplicate surveys.

# Acceptance Criteria

System shall digitize 100% of crop
data entry via offline-capable Android app
within 3 minutes per plot, auto-syncing
when 4G/5G signal exceeds -95 dBm.

Solution must geo-tag each surveyed plot
with ≤ 3 m RMS accuracy
using SBAS-corrected GPS and validate
against pre-loaded Rajasthan land-parcel shapefile.

Platform shall generate finalized Gram Panchayat
Girdawari report in ISO 27001-compliant PDF
with digital signatures, ready for
Patwari submission within 30 minutes.

Training module shall deliver 4-hour competency-based
curriculum in Hindi & Rajasthani,
ensuring 90% of Patwaris pass
post-test with ≥ 80% score.

Backend shall auto-flag data anomalies (missing
crop type, area mismatch >5%) and
push SMS/email alerts to respective
Circle Head within 5 minutes.

System must support concurrent 50,000 village-level
users with <2s page load, 99.9%
monthly uptime, and AES-256 encryption
for all data at rest.

Pilot rollout shall cover 500 villages
across 5 districts, demonstrating 50% reduction
in man-days versus manual process,
verified by independent third-party audit.

# Resources

| Role | Count | Years of Experience | Responsibilities |
| --- | --- | --- | --- |
| Project Director | 1 | 20 | Overall governance, stakeholder alignment, budget control, and MoU enforcement with state. |
| Drone Operations Manager | 2 | 10 | Fleet scheduling, DGCA compliance, pilot rostering, and incident response statewide. |
| AI/ML Engineer | 6 | 5 | Develop NDVI, CHM, and segmentation models; maintain MLOps pipeline and retraining cycles. |
| Geospatial Lead | 2 | 12 | Design photogrammetry workflow, ensure SOI accuracy, and integrate with cadastral fabric. |
| Cloud DevOps Engineer | 4 | 7 | Kubernetes, Terraform, CI/CD, monitoring, cost optimisation, and disaster recovery. |
| Mobile App Developer | 3 | 5 | Build voice-first PWA, offline sync, eSign, and multilingual support. |
| Cybersecurity Consultant | 2 | 8 | Conduct audits, implement Vault PKI, firmware signing, and incident response. |
| Training & Change Manager | 4 | 10 | Design curriculum, conduct TOT, measure adoption, and run incentive programmes. |

# Cost Analysis

| Item | Cost (INR) | Notes |
| --- | --- | --- |
| VTOL Drones & Sensors | ₹28,000,000 | 60 units with spares, RTK, and multi-spectral cameras. |
| Solar Docking Stations | ₹9,600,000 | 30 units with battery swapper, surge protection, and 5-year warranty. |
| Edge GPU Hardware | ₹4,800,000 | Jetson nodes, storage, and rugged enclosures for 12 sites. |
| Cloud Data Lakehouse | ₹6,000,000 | 30 TB/year for 3 years including Trino queries and backup. |
| Software Development | ₹12,000,000 | PWA, AI models, APIs, blockchain audit, and compliance modules. |
| Training & Handover | ₹3,000,000 | Master trainers, VR vans, manuals, and impact surveys. |
| Cybersecurity & Audit | ₹1,800,000 | Red-team, code audit, ISO 27001 certification, and SOC 2 reports. |
| Insurance & Compliance | ₹2,400,000 | DGCA third-party liability, import duties, and regulatory retainers. |
| Program Management | ₹3,600,000 | PMO, governance, risk, and vendor coordination for 18 months. |

# Key Performance Indicators

| Metric | Target | Measurement Method | Frequency |
| --- | --- | --- | --- |
| Average Girdawari Duration | ≤5 days | Timestamp comparison between flight start and report generation | Per Gram Panchayat |
| Orthomosaic RMSE | ≤0.25 m | SOI standard check against 20 ground control points | Per block |
| Crop Classification F1-Score | ≥94% | Confusion matrix from 1000 random field validations | Monthly |
| System Uptime | 99.5% | Prometheus uptime probe for drones, docks, and cloud | Daily |
| Data Entry Error Rate | ≤0.5% | Random audit of 5000 records against source | Quarterly |
| Farmer Satisfaction | ≥80% | IVR survey of 5000 farmers | Semi-annually |
| Cost Savings | ₹12 crore/year | Comparison of historical man-day costs vs platform OpEx | Annually |
| Training Completion | 100% of Patwaris | LMS module completion and certification records | Quarterly |
| Security Vulnerabilities | 0 critical | CERT-In compliant vulnerability scan and red-team report | Monthly |
| Dispute Resolution Time | ≤36 hours | Helpdesk ticket closure timestamp analysis | Weekly |