# AI-Enabled Drone-Based Girdawari Digitization Platform

November 2025

# Contents

# About Company

AIonOS is a global enterprise AI company established in April 2024 as a joint venture between InterGlobe Enterprises (majority stakeholder) and Assago Group. The company represents a strategic alliance that combines InterGlobe's extensive experience in aviation, hospitality, and travel sectors with Assago Group's technology expertise. Headquartered in Singapore, AIonOS maintains operational centers across Noida, Hyderabad, the United States, the United Kingdom, Paris, Africa, and the Middle East, establishing a truly global presence.

The company is co-founded by Rahul Bhatia, Group Managing Director of InterGlobe, and CP Gurnani, former CEO of Tech Mahindra and current Executive Vice Chairman of AIonOS. This leadership combination brings together decades of industry expertise spanning aviation, hospitality, travel, and technology services. Their shared vision focuses on transforming traditional businesses into AI-native enterprises through innovative solutions that address real-world operational challenges.

AIonOS's fundamental mission centers on empowering businesses with advanced AI solutions that streamline workflows and elevate customer experiences. The company is dedicated to enabling enterprises to accelerate their digital transformation journey by enhancing both human capabilities and system functionalities through AI-powered solutions. The organizational culture emphasizes groundbreaking progress, teamwork, and inclusivity, fostering innovation through collaborative efforts across all business units.

The company's flagship offering, the IntelliMate™ platform, serves as a proprietary agentic AI solution that unifies, orchestrates, and observes AI agents within enterprise environments. This platform integrates AI into every decision-making process, delivering tangible business results through task automation and predictive customer analytics. AIonOS provides comprehensive AI-driven solutions including custom IT implementations, industry-specific AI products, data intelligence services, and customer experience transformation tools.

Initially targeting the Travel, Transportation, Logistics, and Hospitality (TTLH) sectors, AIonOS has strategically expanded its services across multiple industries including banking, retail, telecommunications, healthcare, education, and real estate. The company leverages predictive learning technologies using artificial intelligence and machine learning to deliver customized solutions that integrate operations and provide personalized services to end customers.

With a workforce ranging from 51-200 employees and operating within an estimated addressable market of $150 billion, AIonOS maintains significant market presence. The company has established strategic partnerships and made key investments, including the recent acquisition of Cloud Analogy, a Salesforce Summit Partner, to enhance its AI-powered CRM capabilities and expand its global reach.

AIonOS actively pursues strategic partnerships and collaborations to deliver industry-specific solutions at enterprise scale. The company has successfully secured launch customers across its target verticals and continues expanding its technological capabilities through strategic investments and partnership agreements. This approach positions AIonOS as a leading provider of AI-native enterprise solutions, committed to driving digital transformation across diverse industry sectors.

# Problem Statement

Rajasthan’s manual Girdawari demands 300+ man-days per Gram Panchayat.
Patwari covers only 16 fields/day, leading to 312.5 days for 5000 fields.
Outdated paper records cause revenue loss and litigation.
Lack of GPS tagging yields <70% spatial accuracy.
Monsoon dependence shrinks the survey window to 45 days/year.
Multi-village jurisdiction multiplies travel overhead.
Manual entry errors propagate to Bhulekh, credit, and insurance systems.
No real-time visibility for administrators or farmers.
Delayed crop-loss compensation fuels farmer unrest.
Overall administrative cost exceeds ₹2.8 crore per district per cycle.

# Key Challenges

High man-day requirement:
300+ days
per Panchayat
with 16
fields/day throughput.

Spatial inaccuracy: Paper
sketches miss
field boundaries;
<70% overlay
with Bhunaksha.

Data latency:
60–90 days
gap between
survey and
record update.

Resource scarcity: 1
Patwari per 4–5
villages; no
internet, power,
or transport.

Training deficit: 68%
of field staff
lack exposure to
drones, GIS, or
mobile apps.

Climatic constraint: Dust
storms and
pre-monsoon winds
limit drone
flying window.

Change resistance:
Historical manual
process breeds
mistrust in
machine data.

# Our Solution Approach

## Automated Mission Planning

AI converts Bhunaksha polygons into
optimized drone flight paths. Swarm
logic assigns sectors to
multiple drones, ensuring 1000+
fields covered per day.

## Edge AI Crop Classification

On-board GPU runs TensorFlow model
trained on 1.2M Rajasthan crop
images. Real-time NDVI, GLCM,
and CNN fusion classify
crops with 94% accuracy.

## Tamper-Proof Data Capture

Each image hashed with SHA-256
and signed via blockchain wallet.
Metadata includes GNSS-RTK coordinates
(±2 cm) and timestamp
to prevent post-survey edits.

## 4G/5G Sync & Offline Buffer

Drone pushes compressed data to
edge server over 4G; in
no-coverage zones, stores on 1
TB NVMe and uploads upon
landing within village Wi-Fi range.

## AI-Assisted Validation

Patwari dashboard flags anomalies
via traffic-light UI. One-click
accept or field revisit
request reduces validation
effort by 70%.

## Bhulekh Auto-Update

REST APIs write crop, area,
and owner details to Rajasthan
land records DB. Generates XML
for e-Panjiyan and SMS alert
to farmer within 24h.

## Continuous Learning Loop

Validated labels fed back
weekly to retrain models.
Drone firmware and AI
weights updated OTA, improving
accuracy without site visits.

# Architecture Diagram

Architecture Diagram (fallback textual description):
flowchart TD
subgraph Client
  A[Progressive Web App] Node-> B[Patwari Dashboard]
  C[Farmer Portal]
end
subgraph Edge
  D[Drone Swarm] Node-> E[Edge Compute Box]
  E --> F[Local Cache DB]
end
subgraph Gateway
  G[API Gateway] Node-> H[Auth Service]
  G --> I[Data Ingest Service]
end
subgraph Services
  J[AI Inference Svc] Node-> K[GeoServer]
  L[Blockchain Notary] Node-> M[Notification Svc]
  N[Workflow Engine]
end
subgraph Data
  O[PostgreSQL/PostGIS] Node-> P[MinIO Object Store]
  Q[Redis Cache]
end
subgraph Infrastructure
  R[K8s Cluster] Node-> S[Prometheus]
  T[Grafana]
  U[ArgoCD]
end
A --> G
D -.Node4G/Node5G.-> I
I --> J
J --> O
E -.Wi_Fi.-> I
K --> B
L --> M
M --> C
N --> A
O --> P
R --> T

# Technology Stack

DJI M300 RTK

NVIDIA Jetson Xavier NX

TensorFlow Lite

PostGIS

MinIO

Kubernetes

ArgoCD

FastAPI

Redis

React PWA

Keycloak

Hyperledger Fabric

Prometheus

Grafana

OpenFaaS

Python 3.11

GDAL

PyTorch

MQTT

4G LTE Routers

# Key Milestones

| Phase | Duration | Description |
| --- | --- | --- |
| Phase 1 – Survey & Design | 3 weeks | Stakeholder workshops, drone zone clearances, baseline accuracy metrics. |
| Phase 2 – Data Pipeline | 4 weeks | Set up cloud infra, ingest 5TB legacy Bhunaksha, label 50k fields. |
| Phase 3 – AI Model Dev | 5 weeks | Train crop classifier, achieve 94% F1-score; integrate with edge GPU. |
| Phase 4 – Pilot Deployment | 3 weeks | Deploy 3 drones in 1 Panchayat; validate 5-day completion target. |
| Phase 5 – Scale-out | 6 weeks | Cover 4 districts, 120 Panchayats; onboard 60 drones, 200 users. |
| Phase 6 – Integration | 4 weeks | API hooks to e-Panjiyan, e-Sign, and SMS gateway; security audit. |
| Phase 7 – Handover & SLA | 2 weeks | Train state teams, sign 5-year SLA, define penalty clauses. |

# Objectives

Reduce survey man-days
from 300
to 5
per Panchayat
(60× gain).

Achieve ≥94%
crop classification
accuracy and
≥99% area
measurement precision.

Enable real-time
land record
update within
24h of
survey completion.

Cut per-Panchayat
survey cost
from ₹12L
to
₹1.8L.

Provide verifiable,
blockchain-stamped data
for insurance
and
credit.

Create replicable
model for
33 other
districts in
Rajasthan.

Train 500+
Patwaris and
200+ drone
pilots within
12 months.

# Acceptance Criteria

Complete 5000-field
Panchayat in
≤7 calendar
days.

Deliver ≥94%
crop classification
F1-score on
validation set.

Spatial overlap
≥98% with
Bhunaksha field
boundaries.

Data upload and
blockchain hash within
30min of
drone landing.

Dashboard uptime
≥99.5% during
survey
season.

User satisfaction
score ≥4.5/5
in post-survey
feedback.

Zero data loss
incidents during
pilot and
scale-out phases.

# Resources

| Role | Count | Years of Experience | Responsibilities |
| --- | --- | --- | --- |
| Project Manager | 1 | 12 | Plan, risk mgmt, state liaison |
| Solution Architect | 1 | 10 | System design, tech oversight |
| AI/ML Engineer | 3 | 5 | Model dev, edge optimization |
| GIS Expert | 2 | 7 | Bhunaksha alignment, QA |
| Drone Operator | 20 | 3 | Piloting, maintenance, DGCA compliance |
| DevOps Engineer | 2 | 6 | CI/CD, infra, monitoring |
| Training Lead | 1 | 8 | Curate, deliver Patwari training |

# Cost Analysis

| Item | Cost (INR) | Notes |
| --- | --- | --- |
| Drone Fleet (60 units) | ₹9,00,00,000 | DJI M300 RTK with cameras |
| Edge Compute & Sensors | ₹1,20,00,000 | Jetson, batteries, spares |
| Cloud Infra (3 yrs) | ₹75,00,000 | K8s, GPU nodes, storage |
| AI/ML Platform | ₹60,00,000 | Licenses, training GPU |
| Software Development | ₹1,35,00,000 | Apps, APIs, blockchain |
| Training & Documentation | ₹30,00,000 | 500 Patwaris, manuals |
| DGCA Compliance & Insurance | ₹18,00,000 | NPNT, third-party cover |
| Contingency (5%) | ₹67,50,000 | Risk buffer |

# Key Performance Indicators

| Metric | Target | Measurement Method | Frequency |
| --- | --- | --- | --- |
| Survey Duration per Panchayat | ≤7 days | Automated timestamp comparison | Per survey |
| Crop Classification Accuracy | ≥94% | Ground truth vs AI output | Weekly |
| Data Upload Latency | ≤30 min | Drone landing to cloud | Continuous |
| System Uptime | 99.5% | Prometheus probe success | Daily |
| Cost per Panchayat | ₹1.8L | Total spend / Panchayats | Monthly |
| Blockchain Hashes Created | 100% of surveys | Ledger transaction count | Per survey |
| User Satisfaction | ≥4.5/5 | In-app feedback form | Per survey |
| Training Completion Rate | 100% | LMS course status | Quarterly |
| Drone Utilization | ≥80% | Flight hours / available hours | Weekly |
| Data Error Escalations | ≤0.5% | Tickets vs total fields | Monthly |