# Digital Girdawari Solution for Efficient Crop Data Management

November 2025

# Contents

# About Company

AIonOS is a global enterprise AI company established in April 2024 as a joint venture between InterGlobe Enterprises (majority stakeholder) and Assago Group. The company represents a strategic alliance that combines InterGlobe's extensive experience in aviation, hospitality, and travel sectors with Assago Group's technology expertise. Headquartered in Singapore, AIonOS maintains operational centers across Noida, Hyderabad, the United States, the United Kingdom, Paris, Africa, and the Middle East, establishing a truly global presence.

The company is co-founded by Rahul Bhatia, Group Managing Director of InterGlobe, and CP Gurnani, former CEO of Tech Mahindra and current Executive Vice Chairman of AIonOS. This leadership combination brings together decades of industry expertise spanning aviation, hospitality, travel, and technology services. Their shared vision focuses on transforming traditional businesses into AI-native enterprises through innovative solutions that address real-world operational challenges.

AIonOS's fundamental mission centers on empowering businesses with advanced AI solutions that streamline workflows and elevate customer experiences. The company is dedicated to enabling enterprises to accelerate their digital transformation journey by enhancing both human capabilities and system functionalities through AI-powered solutions. The organizational culture emphasizes groundbreaking progress, teamwork, and inclusivity, fostering innovation through collaborative efforts across all business units.

The company's flagship offering, the IntelliMate™ platform, serves as a proprietary agentic AI solution that unifies, orchestrates, and observes AI agents within enterprise environments. This platform integrates AI into every decision-making process, delivering tangible business results through task automation and predictive customer analytics. AIonOS provides comprehensive AI-driven solutions including custom IT implementations, industry-specific AI products, data intelligence services, and customer experience transformation tools.

Initially targeting the Travel, Transportation, Logistics, and Hospitality (TTLH) sectors, AIonOS has strategically expanded its services across multiple industries including banking, retail, telecommunications, healthcare, education, and real estate. The company leverages predictive learning technologies using artificial intelligence and machine learning to deliver customized solutions that integrate operations and provide personalized services to end customers.

With a workforce ranging from 51-200 employees and operating within an estimated addressable market of $150 billion, AIonOS maintains significant market presence. The company has established strategic partnerships and made key investments, including the recent acquisition of Cloud Analogy, a Salesforce Summit Partner, to enhance its AI-powered CRM capabilities and expand its global reach.

AIonOS actively pursues strategic partnerships and collaborations to deliver industry-specific solutions at enterprise scale. The company has successfully secured launch customers across its target verticals and continues expanding its technological capabilities through strategic investments and partnership agreements. This approach positions AIonOS as a leading provider of AI-native enterprise solutions, committed to driving digital transformation across diverse industry sectors.

# Problem Statement

The current manual Girdawari system in Rajasthan is inefficient, resource-intensive, and prone to errors. It requires an estimated 300 man-days for a single Gram Panchayat to complete on-ground execution. The process lacks basic facilities, outdated records, and incomplete data, leading to administrative delays and high workloads.

# Key Challenges

Lack of resources and basic facilities

Outdated records and incomplete data

High workload due to manual data collection and record updating

Administrative delays due to manual bureaucracy

Dependence on traditional methods with minimal technological integration

Training gaps in using modern surveying tools and digital systems

# Our Solution Approach

## Step 1: Digital Data Collection and Record Management

Implement a mobile-based data collection system for Patwaris to collect and update crop details, land records, and other relevant information. This will reduce manual errors, increase data accuracy, and improve the overall efficiency of the Girdawari process.

## Step 2: Automated Report Generation and Analysis

Develop an automated reporting system that can generate accurate and timely reports on crop data, land utilization, and other key metrics. This will enable better decision-making, reduce administrative burdens, and improve the overall effectiveness of the Girdawari process.

## Step 3: Training and Capacity Building

Provide comprehensive training and capacity-building programs for Patwaris to equip them with the necessary skills and knowledge to effectively use the digital data collection and reporting systems. This will address the training gaps and ensure that Patwaris can utilize the new systems efficiently.

# Architecture Diagram

Architecture Diagram (fallback textual description):
graph TD
    subgraph Client
        M[Mobile App] -->|User Input| N[Server]
    end
    subgraph Edge
        O[Server] -->|API Communication| P[Gateway]
    end
    subgraph Gateway
        Q[Gateway] -->|Secure Data Transfer| R[Services]
    end
    subgraph Services
        S[Services Registry] -->|Service Discovery| T[Land Records Service]
        S -->|Service Discovery| U[Crop Details Service]
        S -->|Service Discovery| V[Report Generation Service]
        T -->|Data Processing| W[Data Analytics]
        U -->|Data Processing| W
        V -->|Data Processing| W
        W -->|Report Generation| X[Reporting System]
    end
    subgraph Data
        Y[Database] -->|Data Storage| Z[Data Warehouse]
        Z -->|Data Analysis| AA[Business Intelligence]
    end
    subgraph Infrastructure
        BB[Cloud Infrastructure] -->|Resource Allocation| CC[Containerization]
        DD[Network Security] -->|Threat Detection| EE[Incident Response]
    end
    X -->|Report Sharing| F[Web Portal]
    F -->|Dashboard Access| G[Patwari Dashboard]
    G -->|Admin Access| H[Admin Dashboard]
    H -->|Training Access| I[Training Platform]
    BB -->|Resource Provisioning| CC
    CC -->|Container Management| DD
    EE -->|Security Monitoring| FF[Monitoring Platform]
    FF -->|Alert Notification| GG[Notification System]

# Technology Stack

Mobile App Development (Flutter or React Native)

Server-side Development (Node.js or Django)

Database Management (MySQL or PostgreSQL)

Reporting and Analytics (Power BI or Tableau)

Web Portal Development (React or Angular)

Training Platform (Learning Management System)

# Key Milestones

| Phase | Duration | Description |
| --- | --- | --- |
| Phase 1: Requirements Gathering and System Design | 8 weeks | Conduct thorough requirements gathering, system design, and feasibility studies to ensure that the digital Girdawari solution meets the needs of Patwaris, Gram Panchayats, and other stakeholders. |
| Phase 2: Development and Testing | 16 weeks | Develop the digital data collection and reporting systems, conduct thorough testing, and ensure that the systems meet the required quality and performance standards. |
| Phase 3: Training and Capacity Building | 4 weeks | Provide comprehensive training and capacity-building programs for Patwaris to equip them with the necessary skills and knowledge to effectively use the digital data collection and reporting systems. |

# Objectives

Objective 1: Reduce the time required to complete the Girdawari process by 75%

Objective 2: Improve data accuracy and completeness by 90%

Objective 3: Enhance the overall efficiency of the Girdawari process by 85%

Objective 4: Increase the adoption rate of the digital Girdawari solution among Patwaris by 95%

Objective 5: Reduce the administrative burdens on Gram Panchayats by 80%

# Acceptance Criteria

Criteria 1: The digital data collection system should be able to collect and update crop details and land records with 95% accuracy

Criteria 2: The automated reporting system should be able to generate accurate and timely reports on crop data and land utilization

Criteria 3: The training program should equip Patwaris with the necessary skills and knowledge to effectively use the digital data collection and reporting systems

Criteria 4: The digital Girdawari solution should be able to reduce the time required to complete the Girdawari process by 75%

Criteria 5: The solution should be able to improve data accuracy and completeness by 90%

# Resources

| Role | Count | Years of Experience | Responsibilities |
| --- | --- | --- | --- |
| Project Manager | 1 | 10 | Overall project management, coordination, and delivery |
| Software Developer | 3 | 5 | Development of digital data collection and reporting systems |
| Database Administrator | 2 | 8 | Database design, implementation, and management |
| Training Specialist | 1 | 6 | Development of training programs and capacity-building initiatives |
| Quality Assurance Engineer | 2 | 4 | Testing and quality assurance of the digital Girdawari solution |

# Cost Analysis

| Item | Cost (INR) | Notes |
| --- | --- | --- |
| Development Costs | ₹1,500,000 | Includes costs for software development, database management, and training programs |
| Infrastructure Costs | ₹750,000 | Includes costs for server hosting, database management, and other infrastructure-related expenses |
| Training and Capacity Building | ₹200,000 | Includes costs for training programs, capacity-building initiatives, and other related expenses |

# Key Performance Indicators

| Metric | Target | Measurement Method | Frequency |
| --- | --- | --- | --- |
| Time Required to Complete Girdawari Process | 20 days | Monitor and track the time required to complete the Girdawari process | Monthly |
| Data Accuracy and Completeness | 95% | Regularly review and audit the data collected and reported by Patwaris | Quarterly |
| Adoption Rate of Digital Girdawari Solution | 95% | Monitor and track the number of Patwaris using the digital Girdawari solution | Monthly |
| Administrative Burdens on Gram Panchayats | 80% | Regularly review and audit the administrative burdens on Gram Panchayats | Quarterly |